## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week) | [6 empty] | Week #5 (10 hrs / week) | [6 empty] | Week #6 (10 hrs / week) | [6 empty] | Week #7 (10 hrs / week) | [6 empty] | Week #8 (10 hrs / week) | [6 empty] | Week #9 (10 hrs / week) | [6 empty] | Week #10 (10 hrs / week) | [6 empty] | Week #11 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49 | D50 | D51 | D52 | D53 | D54 | D55 | D56 | D57 | D58 | D59 | D60 | D61 | D62 | D63 | D64 | D65 | D66 | D67 | D68 | D69 | D70 | D71 | D72 | D73 | D74
|  |  |  | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2014-04-06 | 2014-04-07 | 2014-04-08 | 2014-04-09 | 2014-04-10 | 2014-04-11 | 2014-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07
|  |  |  | 145 | 136 | 127 | 118 | 109 | 100 | 91 | 82 | 73 | 64 | 55 | 46 | 37 | 28 | 19 | 10 | 1 | -8 | -17 | -26 | -35 | -44 | -53 | -62 | -71 | -80 | -89 | 0 | -9 | -18 | -27 | -36 | -45 | -54 | -63 | -72 | -81 | -90 | -99 | -108 | -117 | -126 | -135 | -144 | -153 | -162 | -171 | -180 | -189 | -198 | -207 | -216 | -225 | -234 | -243 | -252 | -261 | -270 | -279 | -288 | -297 | -306 | -315 | -324 | -333 | -342 | -351 | -360 | -369 | -378 | -387 | -396 | -405 | -414
|  |  | 160 | 145 | 96 | 103 | 94 | 118 | 114 | 117 | 160 | 131 | 79 | 54 | 13 | 16 | 2 | 14 | 5 | 30 | 12 | 15 | 8 | 6 | 11 | 2 | 2 | 30 | 4 | 11 | 7 | 9 | 4 | 2 | 4 | 5 | 5 | 13 | 123 | 160 | 103 | 141 | 5 | 160 | 94 | 151 | 126 | 0 | 87 | 4 | 14 | 12 | 0 | 11 | 18 | 12 | 4 | 13 | 9 | 3 | 23 | 7 | 19 | 9 | 15 | 22 | 45 | 20 | 89 | 41 | 44 | 64 | 104 | 115 | 160 | 62 | 33
Auto Scaled EC2 Cluster | Design Business Logic | Team | 10 | 145: 5; 136: 2; 127: 5; 118: 2; 109: 2; 100: 2; 91: 3; 82: 6; 73: 2; 64: 2; 55: 2; -72: 1; -81: 2; -90: 5; -99: 10; -117: 32; -126: 0; -135: 1; -144: 2; -162: 5; -396: 5
| Design User Interface | Asha+Swati | 10 | 145: 10; 136: 20; 127: 20; 118: 10; 109: 5; 100: 10; 91: 10; 82: 19; 73: 8; 64: 7; 55: 6; 46: 5; 37: 6; 19: 2; -62: 2; 0: 2; -72: 20; -81: 20; -90: 20; -99: 20; -117: 20; -126: 10; -135: 9; -144: 8; -162: 6; -207: 2; -234: 2; -261: 1; -306: 5; -396: 10
| Design Diagrams | Jumana | 20 | 145: 10; 136: 2; 127: 10; 118: 5; 109: 5; 100: 2; 91: 5; 82: 15; 73: 32; 64: 5; 55: 5; -44: 2; -72: 10; -81: 18; -90: 10; -99: 37; -117: 35; -126: 0; -135: 33; -144: 32; -162: 30; -261: 1; -270: 10; -279: 5; -288: 10; -297: 5; -315: 10; -324: 5; -342: 10; -396: 15
| Implement Front-End Code (Client) | Vijaylaxmi | 20 | 15 | 15 | 10 | 20 | 30 | 10 | 3 | 25 | 20 | 8 | 4 | 8 |  | 2 |  | 5 | 10 | 10 | 5 | 6 | 3 | 5 |  |  | 10 |  | 5 |  | 5 |  |  |  | 5 | 5 | 8 | 20 | 15 | 10 | 20 | 5 | 8 | 30 | 25 | 20 |  | 4 | 4 | 7 | 8 |  | 4 | 8 | 5 |  | 8 | 4 | 1 | 8 |  | 4 | 4 | 10 |  |  |  | 2 | 20 | 20 | 30 | 11 |  | 10 | 10 | 10
| Implement Back-End Code (Admin) | Asha+Swati | 20 | 145: 21; 136: 3; 127: 20; 118: 20; 109: 20; 100: 20; 91: 20; 82: 20; 73: 20; 64: 20; 55: 10; -17: 5; -35: 3; -44: 4; -53: 0; -71: 20; -80: 4; -89: 2; 0: 5; -9: 4; -18: 4; -27: 2; -36: 4; -63: 5; -72: 2; -81: 20; -90: 5; -99: 20; -117: 20; -126: 0; -135: 20; -144: 20; -162: 10; -234: 0; -270: 5; -324: 20; -351: 4; -369: 4; -378: 4; -387: 20; -396: 10; -405: 8; -414: 4
| Booking API | Swati | 10 | 145: 20; 136: 5; 127: 2; 118: 5; 109: 5; 100: 5; 91: 25; 82: 10; 73: 5; 64: 5; 55: 5; 19: 2; 1: 10; -89: 2; -72: 20; -81: 20; -90: 20; -99: 20; -117: 20; -126: 20; -135: 20; -144: 20; -162: 20; -180: 5; -198: 0; -216: 5; -288: 5; -315: 5; -324: 20; -342: 5; -378: 5; -387: 5; -396: 20
| Screen Enhancement | Vijaylaxmi+Jumana | 20 | 145: 20; 136: 10; 127: 10; 118: 10; 109: 10; 100: 40; 91: 20; 82: 10; 73: 20; 64: 20; 55: 20; -71: 0; -89: 2; -72: 10; -81: 20; -90: 10; -99: 0; -117: 5; -126: 5; -135: 10; -144: 0; -162: 10; -225: 6; -243: 5; -342: 20; -351: 5; -387: 20; -396: 15
| Users API | Asha | 10 | 145: 15; 136: 9; 127: 8; 118: 7; 109: 16; 100: 10; 91: 4; 82: 10; 73: 2; 64: 1; 55: 2; -8: 2; -72: 10; -81: 9; -90: 8; -99: 7; -117: 5; -126: 4; -135: 3; -144: 2; -162: 2; -234: 0; -342: 5; -369: 5; -378: 5; -387: 5; -396: 14
| Date-picker component+MVC setup | Vijaylaxmi | 10 | 145: 10; 136: 10; 127: 10; 118: 10; 109: 10; 100: 5; 91: 5; 82: 10; 73: 2; 64: 1; 55: 0; 37: 10; 1: 5; -26: 2; -53: 2; -72: 10; -81: 10; -90: 10; -99: 2; -117: 5; -126: 5; -135: 5; -144: 2; -162: 0; -180: 2; -234: 2; -252: 0; -279: 2; -378: 12; -387: 10; -396: 10
| Search API for vehicles | Vijaylaxmi | 5 | 145: 8; 136: 10; 127: 3; 109: 10; 91: 2; 82: 10; 19: 10; 1: 5; -17: 5; -81: 6; -189: 4; -396: 12
| User UI Screens | Jumana | 5 | 145: 10; -81: 5; -207: 5; -252: 5; -315: 5; -342: 5; -378: 30; -387: 20; -396: 6; -405: 2; -414: 5
| Testing and Integration | Vijaylaxmi+Asha | 10 | -71: 0; -81: 5; -216: 5; -315: 2; -333: 20; -342: 20; -351: 10; -360: 14; -369: 20; -378: 20; -387: 20; -396: 20; -405: 20; -414: 5
| Complete Unit Testing | Team | 5 | -71: 0; -9: 0; -342: 20; -351: 1; -360: 5; -378: 12; -387: 14; -396: 10; -405: 20; -414: 5
| Write Documentation | Jumana+Swati | 5 | 145: 1; 136: 10; 127: 5; 118: 5; 109: 5; 100: 10; 91: 20; 82: 25; 73: 20; 64: 10; 55: 0; -72: 20; -81: 10; -90: 5; -99: 5; -117: 10; -126: 20; -135: 25; -144: 20; -162: 0; -225: 1; -342: 2; -351: 1; -360: 5; -369: 5; -378: 5; -387: 1; -396: 3; -405: 2; -414: 4
Team:
Asha Aher | 10 hours / Week
Jumana Nadir | 10 hours / Week
Swati Narkhede | 10 hours / Week
Vijaylaxmi Nagurkar | 10 hours / Week
Total Available Hours During Sprint: | 160
March 30 -April 6- Spring Break
Ideal Burndown
Remaining Hrs (Total)